| Risk ID | Description | Probability | Impact | Owner | Response Strategy | Status/notes |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | Parking sensors could fail to display parking spot vacancies when they are needed for user to request new spots | Moderate | High impact | Technical Lead | Test sensors before app launch, do a routine check on sensors to ensure max optimality | Open |
| T2 | Parking app could malfunction, not properly synch with gps of user and not display map correctly | Less moderate | Medium impact | App Developer | Test map features in all types of connectivity, provide offline access to printed map of streets and location | Monitoring |
| T3 | Parking app loses connection with parking center API | Moderate | High impact | Backend Developer | Ensure there kiosks in parking lot to use as alternative way to access app | Resolved |
| T4 | Partnering software may fail to process parking payments and billing changes | Moderate | High impact | Software integration lead | Create cash payment system at entry of garage, or implement wait to pay feature | Monitoring |
| S1 | City Approval may take longer than expected, resulting in a delayed use of the parking lot and thus following parking amenities | Low | High Impact | Project Manager | Submit documents for clearance and permission eaerly | Resolved |
| S2 | Parking app functionality may not be completed intime | Moderate | High impact | App developer | Track login development closely and prioritize major authentication features | Monitoring |
| S3 | Parking sensors may arrive too late | Moderate | High | Procurement lead | Order the equipment early and have backups if some break. Use a trusted supplier and Monitor delivery dates | Monitoring |
| S4 | Integration between the app , sensors and API take longer than expected | Moderate | High | Technical Lead | Begin integration testing early and allow extra time for peoples schedules | Monitoring |
| F1 | Payment processing problems can result in reject transaction, leading to empty lots and no business | Moderate | Major | Payment Lead | Test payment processing features(cash, card, credit , debit) before launch of app | Monitoring |
| F2 | Project budget could run out | Low | Major | Project Management | Diligent tracking on project spending, ensure correct allocation of funds and create contingency reserve | Monitoring |
| F3 | Software development costs exceed budget | Moderate | Major | Project Manager | Monitor development hours and compare actual spending with planned budget | Resolved |
| F4 | Price changes of materials or lot space could change budget | Moderate | Major | Projcet Manager | Review pricing on a regular basis , reserving funds for negotiation or any changes | Accepted |
| P1 | Team callouts create gaps that affect project deadlines | Moderate | Major | Project Manager | Examine overall plan with scrutiny , prepare for cases of replacement of individuals, create contingency plans in so plan can continue on time | Monitoring |
| P2 | Developer absence due to emergency (family or personal) | Low | Moderate | Project Manager | Be well versed in the work required to fill position, create space in plan for potential breaks | Monitoring |
| P3 | Vague roles can cause confusion on assignment and cause work to missed entirely or duplicated | Moderate | High | Project Manager | Create clear and precise assignments, having regular team meetups and one on one check ins to ensure team synergy | Monitoring |
| P4 | Poor communication between different teams can cause disruption in the development of the overall project | Moderate | High | Project Management | Ensure established chain of commands, to create linear communication and accountability | Monitoring |

Communication Plan

Daily Standups – Daily

Daily standups will occur daily and consist of development team members who share progress and the blockers that prevented their progress. A next step objective will be given as well. Daily standups will be short around 15 – 30 minutes.

Project Progress meetings – Weekly

Project Manager will host project meeting every week, going over milestones in the progress of projects. In these meetings we will review progress of projects, the accomplishments, risks and deadlines ahead.

Stakeholder meeting – Biweekly to Monthly

Project Manager will present high-level summary presentation of project updates received from daily standups and project progress meetings, as an update to stakeholders of the track of time left over project. In these meetings, any concerns regarding time or budget will be brought to stakeholders’ attention. Updates include the current project status, remaining timeline, major risks, budget concerns, and important milestones.

Any adjustments requested to be made to deliverables will be documented and reviewed. Stakeholder meetings will occur every 2 – 4 weeks.