## Gantt Chart
Parking Management System — Project Gantt Chart
Baseline plan: 16 weeks ¦ September 21, 2026–January 8, 2027 ¦ Dates assume a Monday–Friday workweek
WBS | Workstream | Task / Deliverable | Start | Finish | Workdays | Status | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04
1.1 | Authentication | New user registration | 2026-09-21 | 2026-09-25 | 5 | Planned | ■
1.2 | Authentication | Login (username and password) | 2026-09-24 | 2026-09-30 | 5 | Planned | ■ | ■
1.3 | Authentication | Home page prompt | 2026-09-28 | 2026-10-02 | 5 | Planned |  | ■
2.1.1 | User Management | Add user | 2026-09-28 | 2026-10-02 | 5 | Planned |  | ■
2.1.2 | User Management | Edit user information | 2026-10-01 | 2026-10-06 | 4 | Planned |  | ■ | ■
2.1.3 | User Management | Remove user | 2026-10-05 | 2026-10-08 | 4 | Planned |  |  | ■
2.2.1 | User Management | Add operator | 2026-10-05 | 2026-10-09 | 5 | Planned |  |  | ■
2.2.2 | User Management | Edit operator information | 2026-10-08 | 2026-10-13 | 4 | Planned |  |  | ■ | ■
2.2.3 | User Management | Remove operator | 2026-10-12 | 2026-10-15 | 4 | Planned |  |  |  | ■
2.M | User Management | testing | 2026-10-16 | 2026-10-20 | 3 | Milestone |  |  |  | ■ | ■
3.1 | Front Page | Navigation bar shell | 2026-09-28 | 2026-10-02 | 5 | Planned |  | ■
3.1.1 | Front Page | Home navigation | 2026-10-01 | 2026-10-05 | 3 | Planned |  | ■ | ■
3.1.2 | Front Page | Account navigation | 2026-10-05 | 2026-10-07 | 3 | Planned |  |  | ■
3.1.3 | Front Page | Parking navigation | 2026-10-06 | 2026-10-08 | 3 | Planned |  |  | ■
3.2.1 | Front Page | Parking information display | 2026-10-08 | 2026-10-14 | 5 | Planned |  |  | ■ | ■
3.2.2 | Front Page | Notifications display | 2026-10-12 | 2026-10-16 | 5 | Planned |  |  |  | ■
3.2.3 | Front Page | Permit expiration reminders | 2026-10-26 | 2026-10-29 | 4 | Planned | [5 empty] | ■
3.3.1 | Front Page | Registered vehicles display | 2026-10-15 | 2026-10-20 | 4 | Planned |  |  |  | ■ | ■
3.3.2 | Front Page | Citations display | 2026-10-19 | 2026-10-23 | 5 | Planned |  |  |  |  | ■
3.3.3 | Front Page | Permits display | 2026-10-21 | 2026-10-27 | 5 | Planned |  |  |  |  | ■ | ■
3.3.4 | Front Page | Boots and tows display | 2026-10-26 | 2026-10-30 | 5 | Planned | [5 empty] | ■
3.M | Front Page | Responsive front-page review | 2026-11-02 | 2026-11-04 | 3 | Milestone | [6 empty] | ■
4.1.1 | About Page | Company overview | 2026-10-05 | 2026-10-07 | 3 | Planned |  |  | ■
4.1.2 | About Page | Company services | 2026-10-07 | 2026-10-09 | 3 | Planned |  |  | ■
4.2.1 | About Page | Phone number | 2026-10-12 | 2026-10-12 | 1 | Planned |  |  |  | ■
4.2.2 | About Page | Email address | 2026-10-12 | 2026-10-13 | 2 | Planned |  |  |  | ■
4.2.3 | About Page | Office location | 2026-10-13 | 2026-10-15 | 3 | Planned |  |  |  | ■
4.M | About Page | review | 2026-10-16 | 2026-10-19 | 2 | Milestone |  |  |  | ■ | ■
5.1.1 | Garage / Parking | Vehicles on account | 2026-10-19 | 2026-10-23 | 5 | Planned |  |  |  |  | ■
5.1.2 | Garage / Parking | Add vehicle to permit | 2026-10-22 | 2026-10-29 | 6 | Planned |  |  |  |  | ■ | ■
5.1.3 | Garage / Parking | Register vehicle | 2026-10-26 | 2026-11-02 | 6 | Planned | [5 empty] | ■ | ■
5.2.1 | Garage / Parking | GPS garage location | 2026-11-02 | 2026-11-06 | 5 | Planned | [6 empty] | ■
5.2.2 | Garage / Parking | Link to system registry | 2026-11-02 | 2026-11-11 | 8 | Planned | [6 empty] | ■ | ■
5.M | Garage / Parking | Garage and vehicle integration test | 2026-11-12 | 2026-11-18 | 5 | Milestone | [7 empty] | ■ | ■
5.2.3 | Garage / Parking | Search garages by name or location | 2026-11-09 | 2026-11-13 | 5 | Planned | [7 empty] | ■
5.2.4 | Garage / Parking | Filter garages by availability | 2026-11-30 | 2026-12-04 | 5 | Planned | [10 empty] | ■
6.1.1 | Payment | Select parking space | 2026-11-09 | 2026-11-13 | 5 | Planned | [7 empty] | ■
6.1.2 | Payment | Enter payment information | 2026-11-12 | 2026-11-18 | 5 | Planned | [7 empty] | ■ | ■
6.1.3 | Payment | Process payment | 2026-11-16 | 2026-11-25 | 8 | Planned | [8 empty] | ■ | ■
6.2.1 | Payment | Confirm selected parking space | 2026-11-23 | 2026-11-25 | 3 | Planned | [9 empty] | ■
6.2.2 | Payment | confirm payment details | 2026-11-24 | 2026-11-30 | 5 | Planned | [9 empty] | ■ | ■
6.2.3 | Payment | Procss Payment system | 2026-11-30 | 2026-12-04 | 5 | Planned | [10 empty] | ■
6.M | Payment | Payment test | 2026-12-07 | 2026-12-11 | 5 | Milestone | [11 empty] | ■
7.1.1 | Reporting | Track garage occupancy | 2026-11-16 | 2026-11-23 | 6 | Planned | [8 empty] | ■ | ■
7.1.2 | Reporting | Generate occupancy table | 2026-11-23 | 2026-11-30 | 6 | Planned | [9 empty] | ■ | ■
7.1.3 | Reporting | Display available and occupied spaces | 2026-11-30 | 2026-12-04 | 5 | Planned | [10 empty] | ■
7.1.4 | Reporting | Parking availability status (Available / Limited / Full) | 2026-12-02 | 2026-12-04 | 3 | Planned | [10 empty] | ■
7.2.1 | Reporting | Track parking bills | 2026-11-23 | 2026-11-27 | 5 | Planned | [9 empty] | ■
7.2.2 | Reporting | Generate bills due | 2026-11-30 | 2026-12-04 | 5 | Planned | [10 empty] | ■
7.2.3 | Reporting | Request to mail bill | 2026-12-03 | 2026-12-08 | 4 | Planned | [10 empty] | ■ | ■
7.2.4 | Reporting | Bill dispute option | 2026-12-07 | 2026-12-11 | 5 | Planned | [11 empty] | ■
7.3.1 | Reporting | View parking activity | 2026-12-07 | 2026-12-10 | 4 | Planned | [11 empty] | ■
7.3.2 | Reporting | View payment activity | 2026-12-09 | 2026-12-14 | 4 | Planned | [11 empty] | ■ | ■
7.3.3 | Reporting | View user activity | 2026-12-11 | 2026-12-16 | 4 | Planned | [11 empty] | ■ | ■
7.4.1 | Reporting | Citation selection | 2026-12-07 | 2026-12-09 | 3 | Planned | [11 empty] | ■
7.4.2 | Reporting | Citation price | 2026-12-09 | 2026-12-11 | 3 | Planned | [11 empty] | ■
7.4.3 | Reporting | Citation description | 2026-12-10 | 2026-12-14 | 3 | Planned | [11 empty] | ■ | ■
7.4.4 | Reporting | Citation payment | 46370 | 46374 | 5 | Planned | [12 empty] | ■
7.M | Reporting | Reporting acceptance test | 46377 | 46379 | 3 | Milestone | [13 empty] | ■
8.2 | Release | User acceptance testing | 46391 | 46393 | 3 | Planned | [15 empty] | ■
8.3 | Release | Release and monitoring | 46394 | 46395 | 2 | Milestone | [15 empty] | ■
| Planned start | Planned finish
61 deliverables | 46286 | 46395
Planning note
This baseline assumes a cross-functional team can work in parallel. Milestones represent integration or acceptance gates; holiday staffing and external payment-provider approvals may require contingency time.