## Gantt Chart
Parking Management System — Project Gantt Chart (7-Month Plan)
Revised baseline: September 21, 2026–April 20, 2027 ¦ 7 calendar months ¦ Weekly schedule; proposed dates
WBS | Workstream | Task / Deliverable | Start | Finish | Workdays | Status | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19
1.1 | Authentication | New user registration | 2026-10-12 | 2026-10-19 | 6 | Planned |  |  |  | ■ | ■
1.2 | Authentication | Login (username and password) | 2026-10-16 | 2026-10-26 | 7 | Planned |  |  |  | ■ | ■ | ■
1.3 | Authentication | Home page prompt | 2026-10-22 | 2026-10-28 | 5 | Planned |  |  |  |  | ■ | ■
2.1.1 | User Management | Add user | 2026-10-22 | 2026-10-28 | 5 | Planned |  |  |  |  | ■ | ■
2.1.2 | User Management | Edit user information | 2026-10-27 | 2026-11-04 | 7 | Planned | [5 empty] | ■ | ■
2.1.3 | User Management | Remove user | 2026-11-02 | 2026-11-09 | 6 | Planned | [6 empty] | ■ | ■
2.2.1 | User Management | Add operator | 2026-11-02 | 2026-11-09 | 6 | Planned | [6 empty] | ■ | ■
2.2.2 | User Management | Edit operator information | 2026-11-09 | 2026-11-16 | 6 | Planned | [7 empty] | ■ | ■
2.2.3 | User Management | Remove operator | 2026-11-13 | 2026-11-17 | 3 | Planned | [7 empty] | ■ | ■
2.M | User Management | testing | 2026-11-19 | 2026-11-25 | 5 | Milestone | [8 empty] | ■ | ■
3.1 | Front Page | Navigation bar shell | 2026-10-22 | 2026-10-28 | 5 | Planned |  |  |  |  | ■ | ■
3.1.1 | Front Page | Home navigation | 2026-10-27 | 2026-11-02 | 5 | Planned | [5 empty] | ■ | ■
3.1.2 | Front Page | Account navigation | 2026-11-02 | 2026-11-05 | 4 | Planned | [6 empty] | ■
3.1.3 | Front Page | Parking navigation | 2026-11-04 | 2026-11-09 | 4 | Planned | [6 empty] | ■ | ■
3.2.1 | Front Page | Parking information display | 2026-11-09 | 2026-11-16 | 6 | Planned | [7 empty] | ■ | ■
3.2.2 | Front Page | Notifications display | 2026-11-13 | 2026-11-19 | 5 | Planned | [7 empty] | ■ | ■
3.2.3 | Front Page | Permit expiration reminders | 2027-01-18 | 2027-01-29 | 10 | Planned | [17 empty] | ■ | ■
3.3.1 | Front Page | Registered vehicles display | 2026-11-17 | 2026-11-25 | 7 | Planned | [8 empty] | ■ | ■
3.3.2 | Front Page | Citations display | 2026-11-24 | 2026-11-30 | 5 | Planned | [9 empty] | ■ | ■
3.3.3 | Front Page | Permits display | 2026-11-27 | 2026-12-07 | 7 | Planned | [9 empty] | ■ | ■ | ■
3.3.4 | Front Page | Boots and tows display | 2026-12-04 | 2026-12-11 | 6 | Planned | [10 empty] | ■ | ■
3.M | Front Page | Responsive front-page review | 2026-12-15 | 2026-12-18 | 4 | Milestone | [12 empty] | ■
4.1.1 | About Page | Company overview | 2026-11-02 | 2026-11-05 | 4 | Planned | [6 empty] | ■
4.1.2 | About Page | Company services | 2026-11-05 | 2026-11-09 | 3 | Planned | [6 empty] | ■ | ■
4.2.1 | About Page | Phone number | 2026-11-13 | 2026-11-13 | 1 | Planned | [7 empty] | ■
4.2.2 | About Page | Email address | 2026-11-13 | 2026-11-16 | 2 | Planned | [7 empty] | ■ | ■
4.2.3 | About Page | Office location | 2026-11-16 | 2026-11-17 | 2 | Planned | [8 empty] | ■
4.M | About Page | review | 2026-11-19 | 2026-11-24 | 4 | Milestone | [8 empty] | ■ | ■
5.1.1 | Garage / Parking | Vehicles on account | 2026-11-24 | 2026-11-30 | 5 | Planned | [9 empty] | ■ | ■
5.1.2 | Garage / Parking | Add vehicle to permit | 2026-11-30 | 2026-12-09 | 8 | Planned | [10 empty] | ■ | ■
5.1.3 | Garage / Parking | Register vehicle | 2026-12-04 | 2026-12-15 | 8 | Planned | [10 empty] | ■ | ■ | ■
5.2.1 | Garage / Parking | GPS garage location | 2026-12-15 | 2026-12-21 | 5 | Planned | [12 empty] | ■ | ■
5.2.2 | Garage / Parking | Link to system registry | 2026-12-15 | 2026-12-29 | 11 | Planned | [12 empty] | ■ | ■ | ■
5.M | Garage / Parking | Garage and vehicle integration test | 2026-12-31 | 2027-01-11 | 8 | Milestone | [14 empty] | ■ | ■ | ■
5.2.3 | Garage / Parking | Search garages by name or location | 2027-01-04 | 2027-01-15 | 10 | Planned | [15 empty] | ■ | ■
5.2.4 | Garage / Parking | Filter garages by availability | 2027-02-08 | 2027-02-19 | 10 | Planned | [20 empty] | ■ | ■
6.1.1 | Payment | Select parking space | 2026-12-28 | 2027-01-01 | 5 | Planned | [14 empty] | ■
6.1.2 | Payment | Enter payment information | 2026-12-31 | 2027-01-11 | 8 | Planned | [14 empty] | ■ | ■ | ■
6.1.3 | Payment | Process payment | 2027-01-06 | 2027-01-20 | 11 | Planned | [15 empty] | ■ | ■ | ■
6.2.1 | Payment | Confirm selected parking space | 2027-01-18 | 2027-01-20 | 3 | Planned | [17 empty] | ■
6.2.2 | Payment | confirm payment details | 2027-01-18 | 2027-01-27 | 8 | Planned | [17 empty] | ■ | ■
6.2.3 | Payment | Procss Payment system | 2027-01-27 | 2027-02-02 | 5 | Planned | [18 empty] | ■ | ■
6.M | Payment | Payment test | 2027-02-08 | 2027-02-15 | 6 | Milestone | [20 empty] | ■ | ■
7.1.1 | Reporting | Track garage occupancy | 2027-01-06 | 2027-01-18 | 9 | Planned | [15 empty] | ■ | ■ | ■
7.1.2 | Reporting | Generate occupancy table | 2027-01-18 | 2027-01-27 | 8 | Planned | [17 empty] | ■ | ■
7.1.3 | Reporting | Display available and occupied spaces | 2027-01-27 | 2027-02-02 | 5 | Planned | [18 empty] | ■ | ■
7.1.4 | Reporting | Parking availability status (Available / Limited / Full) | 2027-02-15 | 2027-02-26 | 10 | Planned | [21 empty] | ■ | ■
7.2.1 | Reporting | Track parking bills | 2027-01-18 | 2027-01-25 | 6 | Planned | [17 empty] | ■ | ■
7.2.2 | Reporting | Generate bills due | 2027-01-27 | 2027-02-02 | 5 | Planned | [18 empty] | ■ | ■
7.2.3 | Reporting | Request to mail bill | 2027-02-01 | 2027-02-09 | 7 | Planned | [19 empty] | ■ | ■
7.2.4 | Reporting | Bill dispute option | 2027-02-08 | 2027-02-15 | 6 | Planned | [20 empty] | ■ | ■
7.3.1 | Reporting | View parking activity | 2027-02-08 | 2027-02-12 | 5 | Planned | [20 empty] | ■
7.3.2 | Reporting | View payment activity | 2027-02-10 | 2027-02-18 | 7 | Planned | [20 empty] | ■ | ■
7.3.3 | Reporting | View user activity | 2027-02-15 | 2027-02-22 | 6 | Planned | [21 empty] | ■ | ■
7.4.1 | Reporting | Citation selection | 2027-02-08 | 2027-02-10 | 3 | Planned | [20 empty] | ■
7.4.2 | Reporting | Citation price | 2027-02-10 | 2027-02-15 | 4 | Planned | [20 empty] | ■ | ■
7.4.3 | Reporting | Citation description | 2027-02-12 | 2027-02-18 | 5 | Planned | [20 empty] | ■ | ■
7.4.4 | Reporting | Citation payment | 2027-02-18 | 2027-02-24 | 5 | Planned | [21 empty] | ■ | ■
7.M | Reporting | Reporting acceptance test | 2027-03-01 | 2027-03-04 | 4 | Milestone | [23 empty] | ■
8.2 | Release | User acceptance testing | 2027-04-05 | 2027-04-14 | 8 | Planned | [28 empty] | ■ | ■
8.3 | Release | Release and monitoring | 2027-04-19 | 2027-04-20 | 2 | Milestone | [30 empty] | ■
| Planned start | Planned finish
66 planned deliverables / milestones | 2026-09-21 | 2027-04-20
Seven-month schedule assumption
Revised planning note: seven-month staffing assumption; the schedule is proposed and requires team validation. Extra QA, integration, and handoff activities have been included.
0.1 | Planning | Requirements review and scope baseline | 2026-09-21 | 2026-10-09 | 15 | Planned | ■ | ■ | ■
0.2 | Planning | Architecture and UX planning | 2026-10-05 | 2026-10-30 | 20 | Planned |  |  | ■ | ■ | ■ | ■
8.1 | Quality Assurance | Integration and regression testing | 2027-03-08 | 2027-04-02 | 20 | Planned | [24 empty] | ■ | ■ | ■ | ■
8.1.1 | Quality Assurance | Security, payment, and availability testing | 2027-03-22 | 2027-04-09 | 15 | Planned | [26 empty] | ■ | ■ | ■
8.4 | Release | Project documentation and handoff | 2027-04-12 | 2027-04-20 | 7 | Planned | [29 empty] | ■ | ■